## Sprint Overview
Deterministic Enterprise AI Orchestration — Product Backlog
8-Week Sprint Roadmap ¦ 8 Epics ¦ 52 Issues ¦ 230+ Story Points
Sprint | Weeks | Sprint Theme | Epics Covered | Key Deliverables | User Stories | Story Points | Risk Level | Status
Sprint 1 | Wk 1–2 | Foundation & Edge Security | EPIC 1 | Kong API Gateway, TLS termination, rate limiting, ModSecurity WAF (OWASP CRS), IP filtering, payload size limits, structured request logging | 6 | 34 | HIGH | Planned
Sprint 2 | Wk 2–3 | Identity & Authentication | EPIC 2 | JWT validation middleware, Keycloak SSO OIDC flow, OAuth 2.0 client_credentials for service accounts, tenant_id injection, cross-tenant blocking middleware | 5 | 29 | HIGH | Planned
Sprint 3 | Wk 3–4 | Orchestrator Core — API & Classification | EPIC 3 (Part A) | /ai/request REST endpoint, Pydantic schema validation, request metadata persistence, intent taxonomy YAML, ML intent classifier microservice, content/metadata inspector | 7 | 34 | CRITICAL | Planned
Sprint 4 | Wk 4–5 | Deterministic Routing & Execution Proxy | EPIC 3 (Part B) + EPIC 4 | RoutingMap engine, no-fallback routing enforcement, routing decision audit log, AI service registry, ExecutionProxy handler, response capture, service-to-service proxy enforcement | 9 | 37 | CRITICAL | Planned
Sprint 5 | Wk 5–6 | Governance & Policy Engine | EPIC 5 | Policy DSL/YAML schema, per-request policy evaluator (OPA), data sensitivity enforcement, environment isolation rules, token usage tracking, per-tenant quota system with Redis, quota rejection middleware | 7 | 37 | HIGH | Planned
Sprint 6 | Wk 6–7 | Database Security & Secrets Management | EPIC 6 | PostgreSQL Row Level Security, ORM tenant_id global filter, HashiCorp Vault integration, API key encryption, secrets rotation policy, least-privilege DB roles | 5 | 26 | MEDIUM | Planned
Sprint 7 | Wk 7–8 | AI Guardrails & Output Safety | EPIC 7 | Prompt injection scanner, jailbreak pattern detector, malicious prompt audit logging, JSON schema output validator, PII redaction (Microsoft Presidio), hallucination anomaly guard | 6 | 29 | HIGH | Planned
Sprint 8 | Wk 8 | Observability, Testing & Go-Live | EPIC 8 | Prometheus metrics instrumentation, Grafana dashboards, per-request audit trail, token usage aggregation, end-to-end pytest integration suite, Locust load tests, OWASP ZAP pen test | 7 | 27 | MEDIUM | Planned
TOTALS |  |  |  |  | 52 | 253

## Detailed Backlog
📋 Detailed Issue Backlog — All Sprints
Issue ID | Sprint | Epic | Feature | Issue Title | User Story | Description | Acceptance Criteria | Technologies | Priority | Story Points | Status | Labels
ORK-001 | Sprint 1 | EPIC 1 | API Gateway Setup | Install & configure Kong API Gateway | As a platform admin, I want all AI requests to pass through a secure gateway so traffic can be controlled and validated. | Deploy Kong on Docker/K8s. Set global plugin config. Expose /ai/* routes only. Block all other paths with 404. | All /ai/* requests reach orchestrator. Non-AI routes return 404. Kong admin API secured behind PAM. | Kong Gateway 3.x, Docker, Kubernetes, YAML config | P0-Critical | 8 | Backlog | infra, gateway, P0
ORK-002 | Sprint 1 | EPIC 1 | API Gateway Setup | Configure TLS termination at gateway | As a platform admin, I want TLS enforced at the entry point so all data in transit is encrypted. | Obtain or generate TLS certificate. Configure Kong to terminate HTTPS on port 443. Redirect HTTP 80→443. | HTTP requests redirect to HTTPS. TLS 1.2+ enforced. Certificate is valid, trusted, and auto-renewable. | Kong, Let's Encrypt / cert-manager, OpenSSL, Kubernetes secrets | P0-Critical | 5 | Backlog | security, gateway, P0
ORK-003 | Sprint 1 | EPIC 1 | API Gateway Setup | Implement rate limiting rules per consumer | As a platform admin, I want per-client rate limits so no single tenant can exhaust shared API capacity. | Add Kong rate-limit-advanced plugin per route and per consumer. Set burst and sustained limits via YAML config. | Requests exceeding limit receive 429 with Retry-After header. Limits are configurable per tenant. | Kong rate-limit-advanced plugin, Redis (distributed counter) | P1-High | 5 | Backlog | gateway, infra, P1
ORK-004 | Sprint 1 | EPIC 1 | Web Application Firewall | Integrate ModSecurity WAF with OWASP CRS | As a platform admin, I want a WAF to block injection attacks before they reach the orchestrator. | Deploy ModSecurity 3.x in detection then prevention mode alongside Kong. Load OWASP CRS ruleset v4. | SQL injection payloads blocked with 403. XSS payloads blocked. Legitimate requests pass through without false positives. | ModSecurity 3.x, OWASP Core Rule Set v4, Kong plugin / Nginx | P0-Critical | 8 | Backlog | security, gateway, P0
ORK-005 | Sprint 1 | EPIC 1 | Web Application Firewall | Add payload size limits & IP filtering | As a platform admin, I want oversized or suspicious requests blocked at the perimeter. | Configure max body size (5 MB) in Kong. Maintain IP allowlist/denylist in Kong config. Block private ranges if needed. | Requests >5 MB rejected with 413. Denylisted IPs receive 403. Allowlist-only mode configurable per environment. | Kong, ModSecurity, YAML/JSON policy files | P1-High | 5 | Backlog | security, gateway, P1
ORK-006 | Sprint 1 | EPIC 1 | API Gateway Setup | Add structured request logging pipeline | As a platform admin, I want every inbound request logged for traceability and compliance audit. | Enable Kong http-log plugin. Ship structured JSON logs to central log store. Include tenant_id, path, status, latency. | Every request produces a structured JSON log. Logs contain: timestamp, IP, route, HTTP status, latency_ms, request_id. | Kong http-log plugin, Elasticsearch / Loki, Fluentd / Vector | P1-High | 3 | Backlog | observability, gateway, P1
ORK-007 | Sprint 2 | EPIC 2 | Client Authentication | Implement JWT validation middleware | As a client application, I must authenticate before sending any AI requests. | Build FastAPI middleware that parses and verifies JWT signature, expiry, and issuer on every request. Reject invalid tokens. | Valid JWT passes. Expired JWT → 401. Tampered signature → 401. Missing token → 401. Claims extracted to context. | Python FastAPI, python-jose, OAuth 2.0, JWT RS256 | P0-Critical | 8 | Backlog | security, auth, P0
ORK-008 | Sprint 2 | EPIC 2 | Client Authentication | Integrate Keycloak SSO for human users | As an enterprise user, I want to log in with my corporate SSO credentials and receive a valid token. | Deploy Keycloak 24.x. Configure realm, clients, and role mappings. Wire OIDC authorization code flow. | OIDC login flow completes end-to-end. Keycloak roles map to orchestrator permissions. Token refresh works. | Keycloak 24.x, OIDC, OAuth 2.0, Docker, PostgreSQL (Keycloak DB) | P1-High | 5 | Backlog | security, auth, P1
ORK-009 | Sprint 2 | EPIC 2 | Client Authentication | Provision service account client_credentials flow | As a backend service, I want to authenticate machine-to-machine using a service account. | Register service accounts in Keycloak. Implement OAuth 2.0 client_credentials grant. Issue and validate service JWTs. | Service account obtains access token via POST /token. Token accepted by JWT middleware. Revocation supported. | Keycloak, OAuth 2.0 client_credentials, JWT, python-jose | P1-High | 5 | Backlog | security, auth, P1
ORK-010 | Sprint 2 | EPIC 2 | Tenant Isolation | Inject tenant_id into every request context | As the orchestrator, I need a verified tenant_id on every request to enforce data isolation downstream. | Extract tenant_id claim from validated JWT. Attach to request context object. Propagate to all downstream calls. | tenant_id present in request context for every authenticated call. Requests without valid tenant_id → 401. | FastAPI middleware, JWT claims, Python dataclasses / TypedDict | P0-Critical | 5 | Backlog | security, auth, P0
ORK-011 | Sprint 2 | EPIC 2 | Tenant Isolation | Implement cross-tenant request blocking | As a tenant, I must never be able to access data or trigger AI calls belonging to another tenant. | Add validation layer comparing request tenant_id to resource ownership on every data access. Block mismatches with 403. | Cross-tenant resource access returns 403 and logs a security event. Same-tenant access passes. Unit tests cover boundaries. | FastAPI, PostgreSQL RLS, middleware, pytest | P0-Critical | 6 | Backlog | security, auth, P0
ORK-012 | Sprint 3 | EPIC 3 | AI Request API | Create POST /ai/request REST endpoint | As a client, I want to submit AI requests through a single unified API endpoint. | Build POST /ai/request in FastAPI. Accept JSON body with intent, payload, metadata fields. Return 202 + request_id. | Valid requests return 202 + UUID request_id. Invalid schema returns 422 with field-level detail. Endpoint documented in OpenAPI. | FastAPI, Pydantic v2, PostgreSQL, UUID generation | P0-Critical | 5 | Backlog | orchestrator, api, P0
ORK-013 | Sprint 3 | EPIC 3 | AI Request API | Implement strict request schema validation | As the orchestrator, I need to reject malformed or incomplete requests before they enter the processing pipeline. | Define Pydantic model with required fields: intent (str), payload (dict), sensitivity (enum), tenant_id (str). Validate on every call. | Missing required fields → 422 with field-level errors. Extra unknown fields → rejected. Valid requests pass. | FastAPI, Pydantic v2, JSON Schema, pytest | P0-Critical | 3 | Backlog | orchestrator, api, P0
ORK-014 | Sprint 3 | EPIC 3 | AI Request API | Persist request metadata to PostgreSQL | As the platform, I need a durable, queryable record of every request for audit and tracing. | After validation, write request record to ai_requests table: id, tenant_id, intent, sensitivity, timestamp, status. | Every request has a DB record within 100ms. Records are queryable by request_id and tenant_id. Writes are transactional. | PostgreSQL, SQLAlchemy 2.x, Alembic migrations, UUID | P1-High | 3 | Backlog | orchestrator, database, P1
ORK-015 | Sprint 3 | EPIC 3 | Intent Classification | Define enterprise intent taxonomy in YAML | As a platform admin, I want a controlled, versioned list of valid intents to ensure classification is always deterministic. | Author taxonomy.yaml listing all valid intents with labels, descriptions, and examples. Load at orchestrator startup. Version-controlled. | Taxonomy loads without error. Unknown intent labels are rejected at classifier output. Taxonomy version is logged on startup. | YAML, Python, Pydantic config, Git version control | P0-Critical | 3 | Backlog | orchestrator, config, P0
ORK-016 | Sprint 3 | EPIC 3 | Intent Classification | Build intent classifier microservice | As the orchestrator, I need to assign exactly one validated intent label to every incoming request payload. | Train or configure a zero-shot / few-shot classifier (HuggingFace). Expose as FastAPI microservice. Cache results in Redis. | Classifier returns single intent label. Unknown inputs return 'unclassified'. P95 latency < 100ms. >90% accuracy on test set. | Python, HuggingFace Transformers, FastAPI, Redis cache, scikit-learn, pytest | P0-Critical | 13 | Backlog | orchestrator, ml, P0
ORK-017 | Sprint 3 | EPIC 3 | Intent Classification | Store intent→service mappings in config store | As a platform admin, I want intent-to-service mappings persisted and hot-reloadable without service restart. | Store mappings in intent_routing table or YAML config. Expose admin API to read and update mappings. PAM-protected. | Mappings reloadable without restart. Admin API secured by PAM role. All mapping changes are audit-logged. | PostgreSQL, FastAPI, YAML, Alembic, PAM role check | P1-High | 5 | Backlog | orchestrator, config, P1
ORK-018 | Sprint 3 | EPIC 3 | Content Inspection | Implement metadata and payload content inspector | As the orchestrator, I need to inspect request content for sensitivity markers before any routing decisions. | Scan structured metadata sensitivity field. Optionally scan payload text for PII markers using NER. Propagate sensitivity level. | HIGH sensitivity tag detected and propagated to routing context. PII in payload triggers sensitivity upgrade. All inspections logged. | Python, spaCy NER, regex rules, custom sensitivity rule config | P1-High | 5 | Backlog | orchestrator, security, P1
ORK-019 | Sprint 4 | EPIC 3 | Deterministic Routing | Build RoutingMap engine | As the orchestrator, I must route each request to exactly one pre-approved AI service with no ambiguity. | Implement RoutingMap class. Load intent→service config from store at startup. Resolve target service endpoint per intent. | Each intent resolves to exactly one service. Unmapped intents raise RoutingError with structured detail. No default fallback. | Python, dataclasses, YAML config loader, PostgreSQL intent_routing table | P0-Critical | 8 | Backlog | orchestrator, routing, P0
ORK-020 | Sprint 4 | EPIC 3 | Deterministic Routing | Enforce no-fallback routing policy | As the platform, I need routing to fail loudly rather than silently reroute to an unintended service. | Remove any fallback or default service logic from codebase. Raise structured RoutingError. Return 422 with intent detail to client. | Unmapped intent → 422 with intent name in error body. No request is silently rerouted. Error is logged with full context. | Python, structured error responses, code review checklist | P0-Critical | 3 | Backlog | orchestrator, routing, P0
ORK-021 | Sprint 4 | EPIC 3 | Deterministic Routing | Log routing decisions to audit store | As a compliance auditor, I want to see which service was selected and why for every single request. | After routing resolution, write routing_decision record: request_id, intent, selected_service, service_env, timestamp. | Every request has a routing_decision log entry before execution. Entry queryable by request_id and tenant_id. | PostgreSQL, SQLAlchemy, structured logging, FastAPI lifecycle | P1-High | 3 | Backlog | orchestrator, observability, P1
ORK-022 | Sprint 4 | EPIC 4 | AI Service Proxy | Build ExecutionProxy request handler | As the orchestrator, I must forward validated and routed requests to the correct AI service transparently. | Implement ExecutionProxy class. Accept routed request context + service endpoint. Build outbound HTTP request with auth headers. | Proxy forwards request to correct endpoint. Auth headers (API key / token) injected from Vault. Request body preserved faithfully. | Python httpx, async/await, HashiCorp Vault secrets, service registry | P0-Critical | 8 | Backlog | proxy, orchestrator, P0
ORK-023 | Sprint 4 | EPIC 4 | AI Service Proxy | Capture and normalise AI service response | As a client, I want the AI service response delivered back through the orchestrator in a consistent format. | Proxy reads response from AI service. Normalises to standard response envelope. Returns to client via /ai/request response. | Client receives normalised AI response. Errors from AI service propagated with structured error context. HTTP status preserved. | Python httpx, Pydantic response models, FastAPI response handling | P1-High | 5 | Backlog | proxy, orchestrator, P1
ORK-024 | Sprint 4 | EPIC 4 | AI Service Proxy | Log execution details per proxied request | As a compliance auditor, I want a complete execution record including latency and token counts for every AI call. | After proxy completes, write to execution_log: request_id, service_id, latency_ms, http_status, token_count, timestamp. | Every proxied request has an execution_log entry. Latency measured accurately (httpx elapsed). Token count from response headers. | PostgreSQL, Python time/datetime, SQLAlchemy, structured logging | P1-High | 3 | Backlog | observability, proxy, P1
ORK-025 | Sprint 4 | EPIC 4 | AI Service Proxy | Enforce proxy-only service-to-service communication | As the platform, I need all AI service calls to route through ExecutionProxy with no direct call paths allowed. | Audit codebase to remove direct HTTP calls to AI services. Enforce ExecutionProxy as sole egress. Add integration test coverage. | No code paths bypass ExecutionProxy. Integration tests confirm all AI calls routed via proxy. Code review gate added to CI. | Python, codebase audit, pytest integration tests, GitHub Actions CI | P0-Critical | 5 | Backlog | proxy, security, P0
ORK-026 | Sprint 4 | EPIC 3 | Service Registry | Implement AI service registry CRUD API | As a platform admin, I want a central registry of all authorized AI services that is admin-only editable. | Create service_registry table. Build CRUD FastAPI endpoints secured by PAM admin role. Services include endpoint, auth_type, env. | Admin can register and deactivate services via API. Routing engine reads live from registry. Unregistered service calls blocked. | PostgreSQL, FastAPI, PAM role check, Alembic migrations | P1-High | 5 | Backlog | orchestrator, infra, P1
ORK-027 | Sprint 5 | EPIC 5 | Policy Evaluation | Define policy rule format and YAML DSL | As a platform admin, I want to write governance rules in a human-readable YAML format. | Design YAML policy schema: condition block (IF sensitivity=HIGH, tenant=X) and effect block (THEN allow_onprem_only, deny_cloud). | Policy YAML files parse without error. Invalid policies rejected at startup with descriptive validation error. Schema documented. | YAML, Python Pydantic, custom DSL schema design, JSON Schema | P0-Critical | 5 | Backlog | governance, policy, P0
ORK-028 | Sprint 5 | EPIC 5 | Policy Evaluation | Implement per-request OPA policy evaluator | As the orchestrator, I need all applicable policies evaluated before routing each request. | Integrate OPA (Open Policy Agent) or custom evaluator. Load active policies. Evaluate all matching rules. Emit allow/deny decision. | DENY rules block request with 403 + rule name in error. ALLOW rules pass. All evaluations logged with matched rule ID. | OPA (Rego) or Python policy engine, FastAPI, structured logging | P0-Critical | 8 | Backlog | governance, policy, P0
ORK-029 | Sprint 5 | EPIC 5 | Policy Evaluation | Enforce data sensitivity routing constraints | As a compliance officer, I want HIGH sensitivity requests to only reach approved on-premise AI services. | Add sensitivity check in policy evaluator. If request.sensitivity=HIGH and target_service.env=cloud → deny with 403. | HIGH sensitivity + cloud env service → 403 denial with clear message. LOW sensitivity + cloud → allowed. All decisions logged. | Python, OPA / custom policy engine, service_registry env field | P0-Critical | 5 | Backlog | governance, security, P0
ORK-030 | Sprint 5 | EPIC 5 | Cost Governance | Track token usage per request in usage_log | As a platform admin, I want token consumption recorded for every AI service call for billing and budgeting. | Parse token counts from AI service response body or headers. Write prompt_tokens, completion_tokens to usage_log per request. | Every proxied response has a usage_log entry. Token counts match AI service reported values. Queryable by tenant and date. | PostgreSQL, SQLAlchemy, Python, response parsing | P1-High | 3 | Backlog | governance, observability, P1
ORK-031 | Sprint 5 | EPIC 5 | Cost Governance | Implement per-tenant token quota with Redis | As a platform admin, I want each tenant to have a configurable rolling token quota enforced in real time. | Create quota_config table per tenant. Track rolling 24h token usage in Redis. Check quota before forwarding to ExecutionProxy. | Tenant at quota limit receives 429 with Retry-After. Quota resets on schedule. Admin adjustable via secured API. Redis TTL-based. | PostgreSQL, Redis (sorted set / INCR + TTL), FastAPI, Celery / cron | P1-High | 8 | Backlog | governance, infra, P1
ORK-032 | Sprint 5 | EPIC 5 | Cost Governance | Reject over-quota requests before proxy execution | As the orchestrator, I must stop processing and block requests from tenants who have exceeded their quota. | In resource optimization step before proxy: query Redis quota counter. If over limit, return 429 immediately. Request NOT forwarded. | Over-quota request returns 429 + Retry-After header. Request not forwarded to AI service. Quota event logged with tenant_id. | Python, Redis, FastAPI, structured error response | P0-Critical | 3 | Backlog | governance, P0
ORK-033 | Sprint 5 | EPIC 5 | Policy Evaluation | Enforce environment isolation (dev/staging/prod) | As the platform, I need dev and staging environments to never reach production AI services accidentally. | Add environment field to request metadata. Policy engine checks request.env matches service.env. Mismatch → 403. | Dev request targeting prod service → 403 with environment mismatch error. Matching env → allowed. Logged. | Python, OPA / policy engine, service_registry env field | P1-High | 5 | Backlog | governance, security, P1
ORK-034 | Sprint 6 | EPIC 6 | Data Isolation | Implement PostgreSQL Row Level Security | As the platform, I need database queries to automatically scope results to the requesting tenant with no code-level filtering required. | Enable RLS on all tenant-scoped tables. Create row security policy: USING (tenant_id = current_setting('app.tenant_id')). | Queries from tenant A cannot return rows belonging to tenant B even if WHERE clause omitted. Verified by integration test. | PostgreSQL 15+, SQL policy definitions, pg role management, psql testing | P0-Critical | 8 | Backlog | database, security, P0
ORK-035 | Sprint 6 | EPIC 6 | Data Isolation | Add tenant_id global filter to all ORM queries | As a developer, I want tenant isolation enforced at the ORM layer as a defence-in-depth complement to RLS. | Audit all SQLAlchemy models. Add SQLAlchemy event hook injecting WHERE tenant_id = :current_tenant on all queries automatically. | All ORM queries include tenant_id filter. Test suite confirms zero cross-tenant rows returned. No model bypasses the filter. | SQLAlchemy 2.x event system, Python, pytest | P1-High | 5 | Backlog | database, security, P1
ORK-036 | Sprint 6 | EPIC 6 | Secrets Protection | Integrate HashiCorp Vault for API key storage | As a platform admin, I want all AI service credentials stored in a dedicated secrets manager, not in code or environment files. | Deploy Vault in HA mode. Store AI service API keys as KV secrets. Inject into ExecutionProxy at runtime via hvac Python client. | Zero secrets in source code or .env files. Vault-stored secrets retrieved dynamically at startup. Vault audit log enabled. | HashiCorp Vault 1.x, hvac Python client, Docker, Kubernetes secrets | P0-Critical | 8 | Backlog | security, infra, P0
ORK-037 | Sprint 6 | EPIC 6 | Secrets Protection | Enforce least-privilege DB roles per service | As a security engineer, I want each application service to use a DB role with only the permissions it needs. | Create dedicated PostgreSQL roles per service (orchestrator_rw, audit_ro, classifier_rw). Grant minimum required privileges only. | App DB roles have only required permissions. No application role has superuser or DDL privileges. Confirmed via pg_roles audit. | PostgreSQL GRANT/REVOKE, SQL role management, Alembic (DDL via migration role) | P1-High | 5 | Backlog | database, security, P1
ORK-038 | Sprint 6 | EPIC 6 | Secrets Protection | Implement automated secrets rotation policy | As a security admin, I want AI service API keys rotated automatically on a defined schedule without service downtime. | Configure Vault dynamic secrets or TTL-based leases. Implement rotation trigger. Update service_registry on rotation completion. | Secrets rotate on schedule (e.g., every 30 days). Services receive updated credentials without restart. Old secrets expired in Vault. | HashiCorp Vault dynamic secrets / TTL leases, Python hvac, service registry update | P2-Medium | 5 | Backlog | security, infra, P2
ORK-039 | Sprint 7 | EPIC 7 | Prompt Security | Build prompt injection scanner middleware | As the platform, I must detect and block prompt injection attempts before the payload is forwarded to any AI service. | Build scanner FastAPI middleware. Check payload text against curated injection pattern library. Reject with 400 if pattern matched. | Known injection strings blocked with 400. Benign prompts pass through. Scanner P95 latency < 20ms. Patterns hot-reloadable. | Python, regex pattern library, FastAPI middleware, Redis pattern cache | P0-Critical | 8 | Backlog | ai-guardrails, security, P0
ORK-040 | Sprint 7 | EPIC 7 | Prompt Security | Detect and score jailbreak patterns | As the platform, I need to identify attempts to bypass AI model safety guardrails in submitted prompts. | Maintain jailbreak pattern list (role-play bypass, DAN, ignore-previous-instructions, etc). Score each prompt. Block if score > threshold. | High-risk jailbreak attempts blocked with 400. Medium-risk flagged and logged. Low-risk pass. Threshold configurable per tenant. | Python, NLP pattern matching, risk scoring algorithm, configurable thresholds, Redis | P0-Critical | 5 | Backlog | ai-guardrails, security, P0
ORK-041 | Sprint 7 | EPIC 7 | Prompt Security | Log rejected prompts as security events | As a security auditor, I want every blocked prompt logged with metadata for threat analysis. | On scanner block: write to security_events table with: prompt_hash (SHA-256, not plaintext), pattern matched, tenant_id, timestamp. | Every blocked prompt has a security_event record. Prompt stored as hash only. Events queryable by tenant and date range. | PostgreSQL, Python hashlib (SHA-256), SQLAlchemy, FastAPI | P1-High | 3 | Backlog | ai-guardrails, security, P1
ORK-042 | Sprint 7 | EPIC 7 | Output Validation | Validate AI response against expected JSON schema | As the platform, I need to ensure every AI service response conforms to its registered output schema before delivery to client. | Define Pydantic response model per AI service in service_registry. Validate response body before returning. Reject non-conformant. | Non-conformant AI response → 502 with schema violation detail. Valid responses pass through unchanged. Violations logged. | Python Pydantic v2, JSON Schema, FastAPI response models, service registry schema field | P1-High | 5 | Backlog | ai-guardrails, P1
ORK-043 | Sprint 7 | EPIC 7 | Output Validation | Detect and redact PII in AI service responses | As a compliance officer, I want PII automatically identified and redacted from all AI outputs before delivery to any client. | Integrate Microsoft Presidio. Scan response text for PII entities (SSN, email, phone, names). Replace with [REDACTED:TYPE] placeholder. | SSNs, emails, phone numbers, and names redacted in output. Redaction count logged per request. Added latency < 50ms P95. | Python, Microsoft Presidio, spaCy NER, regex fallback, FastAPI | P1-High | 5 | Backlog | ai-guardrails, security, P1
ORK-044 | Sprint 7 | EPIC 7 | Output Validation | Add hallucination anomaly guard for AI outputs | As the platform, I want to flag and optionally block AI outputs that contain suspicious or impossible content. | Define anomaly rules: impossible future dates, unknown entity refs, contradictory claims. Score output. Block if score > threshold. | Anomalous outputs flagged in log with score. High-confidence anomalies blocked with 502. Threshold configurable. Scoring explainable. | Python, custom scoring rules, Pydantic, configurable threshold, structured logging | P2-Medium | 3 | Backlog | ai-guardrails, P2
ORK-045 | Sprint 8 | EPIC 8 | Logging & Metrics | Instrument FastAPI with Prometheus metrics | As a platform admin, I want real-time metrics on request rates, latency, and error rates exposed for scraping. | Add prometheus-fastapi-instrumentator to FastAPI app. Define custom counters: requests_total, routing_decisions, policy_denials. | GET /metrics returns valid Prometheus text format. Request count, latency histograms, and error rate metrics are visible. | Prometheus, prometheus-fastapi-instrumentator, Python, custom Counter/Histogram | P1-High | 5 | Backlog | observability, infra, P1
ORK-046 | Sprint 8 | EPIC 8 | Logging & Metrics | Build Grafana operational dashboards | As a platform admin, I want visual dashboards showing system health, AI usage, and governance metrics at a glance. | Add Prometheus data source in Grafana. Build dashboards: request rate, p50/p95 latency, error rate, token usage by tenant, policy denials. | Dashboards load without errors. Data refreshes every 30s. Alert thresholds configured on error rate and latency panels. | Grafana 10.x, PromQL, Docker Compose, Grafana provisioning YAML | P1-High | 3 | Backlog | observability, infra, P1
ORK-047 | Sprint 8 | EPIC 8 | Logging & Metrics | Implement immutable per-request audit log | As a compliance auditor, I need an immutable, append-only audit trail of every request lifecycle event. | Write audit_log entry for each lifecycle event: received, validated, classified, routed, executed, returned. Append-only table design. | Every request has ≥5 audit_log entries. Records are append-only (no UPDATE/DELETE). Queryable by tenant_id and date range. | PostgreSQL (append-only design, GRANT INSERT only), SQLAlchemy, FastAPI lifecycle hooks | P0-Critical | 5 | Backlog | observability, security, P0
ORK-048 | Sprint 8 | EPIC 8 | Logging & Metrics | Aggregate and expose token usage via API and dashboard | As a platform admin, I want token usage aggregated per tenant and per service and visible in Grafana. | Query usage_log with GROUP BY tenant_id, service_id, date. Expose via /admin/usage API. Build Grafana panel. | Token usage queryable by tenant and service via API. Grafana panel shows daily and weekly trends. Data < 5 min stale. | PostgreSQL aggregation queries, SQLAlchemy, FastAPI, Grafana, PromQL | P2-Medium | 3 | Backlog | observability, governance, P2
ORK-049 | Sprint 8 | EPIC 8 | Logging & Metrics | Write end-to-end integration test suite | As the engineering team, I want automated tests covering the complete request lifecycle from auth to audit log. | Write pytest integration tests: JWT auth → classification → policy eval → routing → proxy mock → response → audit log verification. | All integration tests pass in CI. Code coverage > 80% for orchestrator paths. Full suite runs in < 5 minutes in GitHub Actions. | pytest, httpx (async test client), respx (mock), Docker Compose (test env), GitHub Actions | P0-Critical | 5 | Backlog | testing, infra, P0
ORK-050 | Sprint 8 | EPIC 8 | Logging & Metrics | Run Locust load tests and document performance baseline | As the platform, I need to validate performance and identify bottlenecks under realistic concurrent load before go-live. | Write Locust scenarios simulating 100 concurrent tenants. Run 10-minute sustained test. Capture p50, p95, p99 latency and error rate. | P95 latency < 500ms at 100 concurrent users. Error rate < 0.1%. Throughput > 200 req/s. Results documented in performance report. | Locust 2.x, Python, Grafana (live monitoring during test), Docker | P1-High | 5 | Backlog | testing, infra, P1
ORK-051 | Sprint 8 | EPIC 8 | Logging & Metrics | Execute OWASP ZAP security penetration test | As a security engineer, I want the platform scanned for exploitable vulnerabilities and all critical findings remediated before go-live. | Run OWASP ZAP automated active scan. Perform manual auth bypass, tenant isolation, and injection tests. Remediate critical/high findings. | Zero unresolved Critical or High OWASP findings at go-live. Pen test report produced. All findings triaged with resolution evidence. | OWASP ZAP 2.x, Burp Suite, manual testing, remediation patches, GitHub Issues (findings tracking) | P0-Critical | 5 | Backlog | security, testing, P0
ORK-052 | Sprint 8 | EPIC 8 | Logging & Metrics | Go-live readiness checklist and sign-off | As the project lead, I want a formal readiness checklist completed and signed off before production launch. | Complete checklist covering: all P0 issues resolved, pen test clear, load test baseline met, runbooks written, on-call rotation set up. | Checklist 100% complete. Signed off by engineering lead and security lead. Runbook accessible. Rollback plan documented. | Confluence / Notion (runbooks), GitHub Projects (checklist), Slack (stakeholder notification) | P0-Critical | 4 | Backlog | infra, P0

## Epic Summary
🗂 Epic Summary & Technology Stack
Epic | Title | Description | Core Technologies | Sprints | Issues | Story Points | Priority
EPIC 1 | Edge Security Layer | Secure all inbound traffic before it reaches the orchestrator. Enforce TLS, rate limiting, WAF protection, IP filtering, and structured logging at the network perimeter. | Kong Gateway 3.x, ModSecurity OWASP CRS v4, Let's Encrypt / cert-manager, Redis, Nginx, Docker, Kubernetes, Elasticsearch / Loki | Sprint 1 | 6 | 34 | P0-Critical
EPIC 2 | Identity & Authentication | Authenticate every client and service. Enforce tenant isolation and ensure no cross-tenant data leakage through robust IAM integration with Keycloak. | Keycloak 24.x, OAuth 2.0, OIDC, JWT RS256, python-jose, FastAPI middleware, PostgreSQL (Keycloak DB) | Sprint 2 | 5 | 29 | P0-Critical
EPIC 3 | AI Service Orchestrator Core | Central control plane: REST API, schema validation, intent taxonomy, ML classifier, content inspection, deterministic routing map, service registry, and routing audit log. | FastAPI, Pydantic v2, PostgreSQL, SQLAlchemy 2.x, Alembic, HuggingFace Transformers, scikit-learn, Redis, YAML config | Sprints 3–4 | 10 | 52 | P0-Critical
EPIC 4 | Execution Proxy | Forward validated requests to AI services and capture responses. Sole egress point for all AI calls. No direct service-to-service calls allowed outside this proxy. | Python httpx, async/await, FastAPI, HashiCorp Vault (secret injection), service registry, structured logging, pytest | Sprint 4 | 4 | 21 | P0-Critical
EPIC 5 | Governance & Policy Engine | Evaluate governance rules on every request. Enforce data sensitivity, environment isolation, and cost controls. Block non-compliant requests before execution. | OPA (Open Policy Agent / Rego), Python, YAML policy DSL, PostgreSQL, Redis (quota counters), Celery / cron, FastAPI | Sprint 5 | 7 | 37 | P0-Critical
EPIC 6 | Database Security & Secrets | Protect stored data via Row Level Security, tenant-scoped ORM filters, encrypted secrets management, least-privilege DB roles, and automated secrets rotation. | PostgreSQL 15+ RLS, SQLAlchemy 2.x event hooks, HashiCorp Vault 1.x, hvac Python client, Kubernetes secrets, pg role management | Sprint 6 | 5 | 26 | P0-Critical
EPIC 7 | AI Guardrails | Prevent prompt injection, jailbreaks, PII leakage, and hallucinated outputs with safety middleware applied to both inputs and outputs of every AI service call. | Python, Microsoft Presidio, spaCy NER, regex pattern library, custom risk scorer, Pydantic v2, FastAPI middleware, Redis pattern cache | Sprint 7 | 6 | 29 | P1-High
EPIC 8 | Observability & Launch Readiness | Instrument with Prometheus metrics, Grafana dashboards, and an append-only audit log. Validate with integration tests, load tests, and security pen testing before go-live. | Prometheus, prometheus-fastapi-instrumentator, Grafana 10.x, PromQL, pytest, httpx, respx, Locust 2.x, OWASP ZAP, Burp Suite, GitHub Actions | Sprint 8 | 7 | 27 | P1-High

## Tech Stack
⚙️ Technology Stack Reference
Category | Technology | Version / Notes | Used In | Purpose
API Framework | FastAPI | 0.111+ | All Epics | Primary web framework for orchestrator REST API and internal microservices
Data Validation | Pydantic | v2.x | EPIC 3,4,5,7 | Request schema validation, response models, policy config parsing
API Gateway | Kong Gateway | 3.x | EPIC 1 | Single entry point, TLS termination, rate limiting, routing, logging
WAF | ModSecurity + OWASP CRS | 3.x + CRS v4 | EPIC 1 | Web Application Firewall blocking injection and XSS attacks
Identity Provider | Keycloak | 24.x | EPIC 2 | SSO, OAuth 2.0 / OIDC, JWT issuance, role management
Auth Protocol | OAuth 2.0 / OIDC | RFC 6749 | EPIC 2 | Authentication for both human users and machine service accounts
Auth Token | JWT (RS256) | RFC 7519 | EPIC 2,3 | Signed tokens carrying identity claims and tenant context
Database | PostgreSQL | 15+ | EPIC 3,5,6 | Primary relational store: requests, routing, audit, quota, registry
ORM | SQLAlchemy | 2.x | EPIC 3,4,5,6 | Database access layer with tenant_id global filter hooks
DB Migrations | Alembic | 1.13+ | EPIC 3,6 | Schema versioning and migration management for PostgreSQL
ML / NLP | HuggingFace Transformers | 4.x | EPIC 3 | Zero-shot intent classification and NLP model serving
Cache / Queue | Redis | 7.x | EPIC 1,3,5,7 | Rate limit counters, quota tracking, intent classification cache
Policy Engine | OPA (Open Policy Agent) | 0.65+ | EPIC 5 | Declarative policy evaluation using Rego policy language
Secrets Manager | HashiCorp Vault | 1.16+ | EPIC 4,6 | Secure storage, dynamic secrets, and automated rotation of API keys
PII Detection | Microsoft Presidio | 2.x | EPIC 7 | PII entity recognition and redaction in AI outputs
NER | spaCy | 3.7+ | EPIC 3,7 | Named entity recognition for content inspection and PII detection
Async HTTP | httpx | 0.27+ | EPIC 4 | Async HTTP client for ExecutionProxy AI service calls
Metrics | Prometheus | 2.x | EPIC 8 | Time-series metrics collection and alerting
Dashboards | Grafana | 10.x | EPIC 8 | Operational dashboards with PromQL data source
Testing | pytest + httpx | 8.x + 0.27+ | EPIC 8 | Unit, integration, and end-to-end test suite
Load Testing | Locust | 2.x | EPIC 8 | Performance baseline and concurrency testing
Security Scan | OWASP ZAP | 2.15+ | EPIC 8 | Automated vulnerability scanning for web application security
Container | Docker + Kubernetes | Latest | All Epics | Container runtime and orchestration for all platform services
CI/CD | GitHub Actions | Latest | All Epics | Continuous integration, test execution, and deployment pipeline
Log Aggregation | Loki / Elasticsearch | Latest | EPIC 1,8 | Centralized log storage and search for request audit trail